## Sheet1
No. | Tasks Name | Main Responsible | Week (20/2 - 5/4)
|  |  | W1(20-26/2 | W2(27-5/3) | W3(6-12/3) | W4(13-19/3) | W5(20-26/3) | W6(27-2/4) | W7(3-5/3)
1 | Progress Control Meeting (KEY POINTS) |  | 20/2 | 28/2 | 7/3
2 | Definition of the Problem | Tran Hong Tem, Giang Thu Duyen
3 | Requirement analysis
| Find out the problem | All
| 3.1 Function requirement | Tran Hong Tem
| 3.2 Overview of Processes involved in the system | Giang Thu Duyen
| 3.3 Hardware and Software required | Giang Thu Duyen
| 3.4 Customer’s Acceptance Criteria | Truong Hung Vu, Tran Huu Phuc
4 | Design
| 4.1 Designing the GUI Standards (Java Swing/ JavaFX) | Tran Huu Phuc
| 4.2 Designing E-R Diagram | Giang Thu Duyen
| 4.3 Designing Database Diagram | …
| 4.4 Designing the Database in SQL Server | …
| 4.5 Collecting Employee/Reader/Catalog &Books data | Truong Hung Vu
| 4.5 Designing the Process Module (DFD, Flowchart) | Tran Hong Tem, Giang Thu Duyen, Truong Hung Vu
| 4.6 Designing Coding Standards | Giang Thu Duyen…
5 | Development
5.1 User Interface Programming
- Login
- Reader (Borrowed/Extension/ Search/ Register a Discussion Room/ Feedback)
- Librarian (Reader/Discussion Room/Borrow/ Return management)
- Manager (Catalog books & books/Bookshelf/ Employee/Statistics)
| - Home Page | Tran Huu Phuc
5.2 Functional Programming & Event handling
- Reader
+ Search Document
+ Borrowed Document/ Extention
+ Displays about Extension Document Information
+ Register to Borrow a Discussion Room
+ Feedback Form
- Librarian
+ Add/Update/Delete/Search Reader
+ Add/Update/Delete/Search Discussion Room
+ Add/Update/Search/Extension Borrow Books
+ Search/Displays Return Books
- Manager
+ Add/Update/Delete Catalog Books
+ Add/Update/Delete Books
+ Add/Update/Delete BookShelf
+ Add/Update/Delete Employee
+ Statistics Report
5.3 White Box Test
6 | Evaluation/Testing
7 | Implementation
8 | Maintenance